Future Doctor Initiative

JPS Partnership and BLS Workshop Plan

Document: Summary explaining the confirmed partnership, expected attendance, logistics, and cost structure

——————————————————————————————————————————————————

Table of Contents:

1. Partnership Overview

2. Workshop Purpose

3. Expected Attendance

4. Leadership Team and Volunteers

5. Venue and Logistics

6. Cost Structure

7. Event Requirements

8. Next Steps

9. Contact Details

——————————————————————————————————————————————————

1-Partnership Overview:-

• Future Doctor Initiative has secured Jordan Paramedic Society (JPS) as a partner to provide Basic Life Support (BLS) courses for our first workshop cycle.

• JPS will support the workshop by providing the trainer, the required training equipment, and the practical materials needed for the BLS course.

• This partnership allows FDI to deliver a safer and more credible medical awareness workshop to students, team members, volunteers, and participants.

2-Workshop Purpose:-

• The purpose of the workshop is to train participants on basic emergency response and BLS skills in a professional and practical setting.

• The workshop aims to improve confidence, awareness, and safe response during basic medical emergencies.

• The course will be delivered with the support of JPS to make sure the medical information and practical training are supervised properly.

3-Expected Attendance:-

| Category | Expected Number / Details |
| --- | --- |
| Participants | 35 expected participants |
| FDI team members | 12 team members expected to attend and support the event |
| Volunteers | Volunteers will support registration, organization, participant guidance, media, and general event flow |
| JPS trainer / representative | Provided by JPS as part of the BLS course arrangement |
| Total attendance estimate | Around 48+ people depending on final volunteers and partner attendance |

4-Leadership Team and Volunteers:-

• The FDI leadership team will manage the workshop preparation, communication, logistics, media coverage, participant registration, and on-site organization.

• The current named leadership members are listed below. Two additional team or volunteer names can be added once finalized.

| Role | Name |
| --- | --- |
| President | Shihab Ghandi |
| Co-President | Mohammed Ghandi |
| Head of Operations | Sulaiman Ghandi |
| Deputy Head of Operations | Sanad Lada |
| Head of Organization | Haya Rihani |
| Deputy Head of Organization | Luna Zaatar |
| Head of Media | Tala Qiblawi |
| Deputy Head of Media | Anirudh Nagella |
| Co-Head of Education | Mohammad Mazen |
| Co-Head of Education | Mayasa Zaatar |
| Additional Team Member / Volunteer | To be confirmed |
| Additional Team Member / Volunteer | To be confirmed |

5-Venue and Logistics:-

• FDI plans to host the event in a hotel or professional venue such as Geneva Hotel.

• The expected venue requirement is one room for 6 hours to allow time for setup, registration, training, breaks, and closing.

• The event will include one coffee break for participants, team members, volunteers, and relevant guests if included in the final count.

• The venue should provide a suitable training room, seating arrangement, projector or screen if needed, and enough space for practical BLS demonstrations.

6-Cost Structure:-

| Item | Cost | Details |
| --- | --- | --- |
| JPS BLS course | 10 JD per participant | Includes trainer, equipment, and practical BLS training support |
| Coffee break | 7 JD per person | One coffee break expected through Geneva Hotel or similar venue |
| Training room | One room for 6 hours | Final price depends on the hotel agreement and room package |
| Participants expected | 35 participants | Used as the main planning number |
| Team members | 12 team members | Expected to support the workshop on event day |

• Estimated JPS training cost for 35 participants: 35 × 10 JD = 350 JD.

• Estimated coffee break cost for 35 participants only: 35 × 7 JD = 245 JD.

• Estimated coffee break cost if 35 participants + 12 team members are included: 47 × 7 JD = 329 JD.

• Final total will depend on whether team members, volunteers, JPS representatives, and guests are included in the coffee break count, and on the final room price agreed with the hotel.

7-Event Requirements:-

• Confirm the final venue and room booking for 6 hours.

• Confirm the exact number of participants, team members, volunteers, and guests before finalizing the hotel count.

• Confirm with JPS the trainer, equipment, BLS course structure, timing, and any certificate details.

• Prepare registration, attendance sheets, participant communication, and on-site team assignments.

• Prepare media coverage and branding while making sure all public representation is approved by FDI leadership and JPS when relevant.

8-Next Steps:-

• Finalize the participant number and confirm whether the expected attendance remains 35 participants.

• Confirm with Geneva Hotel or another suitable hotel the room price, availability, and coffee break package.

• Confirm the final JPS agreement in writing, including the 10 JD per participant price and what it includes.

• Create a final event-day schedule covering setup, registration, training, coffee break, closing, and cleanup.

• Assign volunteers and leadership members to clear roles before the event day.

9-Contact Details:-

• FDI Email: FDI.jo123@gmail.com

• President: Shihab Ghandi

• President Email: ghandishihab1@gmail.com

• Co-President: Mohammed Ghandi

• Co-President Email: Mohamedghandimohamed@gmail.com

Good luck everyone!